## General
Tom And Jerry In Maze Game
TEAM 55 (Member) | Tim Law
Kelly Lam
| Kelly Lo |  |  |  | Project Start | 2023-09-23 | 0 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9
| ALL |  |  |  | Display Week | 0 | 2023-09-23 | [6 empty] | 2023-09-30 | [6 empty] | 2023-10-07 | [6 empty] | 2023-10-14 | [6 empty] | 2023-10-21 | [6 empty] | 2023-10-28 | [6 empty] | 2023-11-04 | [6 empty] | 2023-11-11 | [6 empty] | 2023-11-18 | [6 empty] | 2023-11-25
 | time axis 2023-09-23 to 2023-12-01
TASK | Main PIC | PIC #2 | Progress | START | END | time axis 2023-09-23 to 2023-12-01
Activity 1 | ALL |  | 100% | 2023-09-23 | 2023-10-13
Sign up Group Formation | Tim Law |  | 100% | 2023-09-23 | 2023-09-25
Team Repo Setup on GitHub | Tim Law |  | 100% | 2023-09-23 | 2023-09-25
Data Modeling | ALL |  | 100% | 2023-10-06 | 2023-10-13
Class Diagram | ALL |  | 100% | 2023-10-06 | 2023-10-13
Use Case Specification | ALL |  | 100% | 2023-10-10 | 2023-10-13
Activity 2 | ALL |  | 100% | 2023-09-23 | 2023-11-26 | bar: 2023-09-23
Project Management Documents | ALL |  | 100% | 2023-11-05 | 2023-11-26
Meeting Minutes | Kelly Lo |  | 100% | 2023-09-23 | 2023-11-26
Gantt Chart | Kelly Lo |  | 100% | 2023-09-23 | 2023-11-26
Burndown Chart | Tim Law |  | 100% | 2023-09-23 | 2023-11-26
Git Commit Log | Tim Law |  | 100% | 2023-11-05 | 2023-11-26
Documentation with JavaDoc | ALL |  | 100% | 2023-11-05 | 2023-11-26
Screenshots of Application Software | Tim Law |  | 100% | 2023-11-06 | 2023-11-26
Entire Project Quality | ALL |  | 100% | 2023-11-05 | 2023-11-26
Teamwork Performance | ALL |  | 100% | 2023-11-05 | 2023-11-26
YouTube Video Demo | ALL |  | 100% | 2023-11-13 | 2023-11-26
Functional Programming Quality | ALL |  | 100% | 2023-11-05 | 2023-11-21
Function A - Maze Generator | Kelly Lo |  | 100% | 2023-11-05 | 2023-11-14
Function B - Shortest Path | Tim Law |  | 100% | 2023-11-06 | 2023-11-14
Function C - Tom catches Jerry in Maze Game | Kelly Lam |  | 100% | 2023-11-08 | 2023-11-14
Function D - Unit Testing with Converage Report | ALL |  | 100% | 2023-11-15 | 2023-11-21

## Indivdual
Individual Task (Main PIC only) | Individual Progress | Deadline | Dependency
ALL | 100% | 2023-11-26
Activity 1 | 100% | 2023-10-13
Activity 2 | 100% | 2023-11-26
Class Diagram | 100% | 2023-10-13
Data Modeling | 100% | 2023-10-13
Documentation with JavaDoc | 100% | 2023-11-26
Entire Project Quality | 100% | 2023-11-26
Function D - Unit Testing with Converage Report | 100% | 2023-11-21
Functional Programming Quality | 100% | 2023-11-21
Project Management Documents | 100% | 2023-11-26
Teamwork Performance | 100% | 2023-11-26
Use Case Specification | 100% | 2023-10-13 | Function A&B
YouTube Video Demo | 100% | 2023-11-26
Kelly Lam | 100% | 2023-11-14
Function C - Tom catches Jerry in Maze Game | 100% | 2023-11-14
Kelly Lo | 100% | 2023-11-26
Function A - Maze Generator | 100% | 2023-11-14
Gantt Chart | 100% | 2023-11-26
Meeting Minutes | 100% | 2023-11-26 | Function A
Tim Law | 83.33% | 2023-11-26
Burndown Chart | 100% | 2023-11-26
Function B - Shortest Path | 100% | 2023-11-14
Git Commit Log | 0% | 2023-11-26
Screenshots of Application Software | 100% | 2023-11-26
Sign up Group Formation | 100% | 2023-09-25
Team Repo Setup on GitHub | 100% | 2023-09-25
(blank) |  |  | Functional Programming Quality
(blank)
Grand Total | 95.45% | 2023-11-26

## Info
Within 3 Days from Deadline
Finished
To be Finished
Unfinished Passed Deadline