## Data & Chart
| Job Catalogs | Job ID | Job Details | Initial Estimate (in Hours) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Hours Left
Activity 1 | Project Initiation Setup (110) | 111 | Sign up Group Formation | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 112 | Team Repo Setup on GitHub | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data Modeling (120) | 121 | Class Diagram | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 122 | Use Case Specification | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2 | Project Management Documents (210) | 211 | Meeting Minutes | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0
|  | 212 | Gantt Chart | 1 | 0.4 | 0.2 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.04 | 0.06 | 0
|  | 213 | Burndown Chart | 1 | 0.4 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.04 | 0
|  | 214 | Git Commit Log | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0
|  | 215 | Documentation with JavaDoc | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
|  | 216 | Screenshots of Application Software | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| Entire Project Quality (220) | 221 | Teamwork Performance (Group Evaluation) | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0
|  | 222 | YouTube Video Demo | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
| Functional Programming Quality (230) | 231 | Function A - Maze Generator | 10 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0
|  | 232 | Function B - Shortest Path | 10 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0
|  | 233 | Function C - Tom catches Jerry in Maze Game | 10 | 0 | 0 | 0 | 0 | 2 | 6 | 2 | 0 | 0 | 0
|  | 234 | Function D - Unit Testing with Converage Report | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 0 | 0
Setting | Start | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Planned Hours |  | 7.05 | 7.05 | 7.05 | 7.05 | 7.05 | 7.05 | 7.05 | 7.05 | 7.05
Actual Hours |  | 6.8 | 7.78 | 0.14 | 0.14 | 13.14 | 15.64 | 10.64 | 5.57 | 3.6
Remaining Effort | 63.45 | 56.65 | 48.87 | 48.73 | 48.59 | 35.45 | 19.81 | 9.17 | 3.6 | 0
Ideal Burndown | 63.45 | 56.4 | 49.35 | 42.3 | 35.25 | 28.2 | 21.15 | 14.1 | 7.05 | 1.0658e-14